## Sheet1
PPAP Tracker | [19 empty] | FMT NO.
REV NO.
PAGE
| PART NO. | 40256626 TRMF |  | 40257237 |  | 40229265 |  | 40102994 |  | 40256626 CKMF |  | 40286128 Tesla |  | 40269907 |  | 40280398 |  | 40280399 |  | 40286128 |  | FSI
| PPAP NO. | [8 empty] | 66266 |  | 69166 |  | 68093 |  | 68133 |  | 69011 |  | 69166
Element Number | Element Description | Status | Due Date | Status | Due Date | Status | Due Date | Status | Due Date | Status | Due Date | Status | Due Date | Status | Due Date | Status | Due Date | Status | Due Date | Status | Due Date
1 | Supplier Timing | Completed | 2025-12-05 | Completed | - | Completed | - | Completed | - | Completed | - | Completed | - | Completed | 2026-03-12 | Completed | 2026-03-30 | Completed | 2026-04-24 | Completed | 2026-06-04
2 | Fixtures/Tooling/Gaging | Completed | 2025-12-05 | Completed | - | Completed | - | Completed | - | Completed | - | Completed | - | Completed | 2026-03-12 | Completed | 2026-04-11 | Completed | 2026-05-06 | Completed | 2026-06-24
3 | Supply Chain Map | Completed | 2025-12-05 | Completed | - | Completed | - | Completed | - | Completed | - | Completed | - | Completed | 2026-03-12 | Completed | 2026-03-30 | Completed | 2026-04-24 | Completed | 2026-05-20
4 | Tiered Risk Assessment | Completed | 2025-12-05 | Completed | - | Completed | - | Completed | - | Completed | - | Completed | - | Completed | 2026-03-12 | Completed | 2026-03-30 | Completed | 2026-04-24 | Completed | 2026-05-20
5 | DFMEA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
6 | DVP | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
7 | Design Record | Completed | 2025-11-20 | Completed | - | Completed | - | Completed | - | Completed | - | Completed | - | Completed | 2026-03-12 | Completed |  | Completed | 2026-05-06 | Completed | 2026-05-20
8 | Process Flow | Completed | 2025-12-01 | Completed | - | Completed | - | Completed | - | Completed | - | Completed | - | Completed | 2026-03-12 | Completed | 2026-05-06 | Completed | 2026-05-06 | Completed | 2026-06-24
9 | Floor Plan Layout | Completed | 2025-12-01 | Completed | - | Completed | - | Completed | - | Completed | - | Completed | - | Completed | 2026-03-12 | Completed | 2026-04-11 | Completed | 2026-05-06 | Completed | 2026-06-24
10 | PFMEA | Completed | 2025-12-01 | Completed | - | Completed | - | Completed | - | Completed | - | Completed | - | Completed | 2026-03-12 | Completed | 2026-04-11 | Completed | 2026-05-06 | Completed | 2026-06-24
11 | Process Control Plan | Completed | 2025-12-01 | Completed | - | Completed | - | Completed | - | Completed | - | Completed | - | Completed | 2026-03-12 | Completed | 2026-05-18 | Completed | 2026-05-18 | Completed | 2026-07-29
12 | PM Plan | Completed | 2025-12-01 | Completed | - | Completed | - | Completed | - | Completed | - | Completed | - | Completed | 2026-03-12 | Completed | 2026-04-11 | Completed | 2026-05-06 | Completed | 2026-06-24
13 | Error proofing | Completed | 2025-12-01 | Completed | - | Completed | - | Completed | - | Completed | - | Completed | - | Completed | 2026-03-12 | Completed | 2026-04-11 | Completed | 2026-05-06 | Completed | 2026-06-24
14 | Vision Systems | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
15 | Operator Instructions | Completed | 2025-12-02 | Completed | - | Completed | - | Completed | - | Completed | - | Completed | - | Completed | 2026-03-12 | Completed | 2026-05-18 | Completed | 2026-05-18 | Completed | 2026-07-29
16 | Visual Aids | Completed | 2025-12-02 | Completed | - | Completed | - | Completed | - | Completed | - | Completed | - | Completed | 2026-03-12 | Completed | 2026-05-18 | Completed | 2026-05-18 | Completed | 2026-07-29
17 | MSA | Completed | 2025-12-02 | Completed | - | Completed | - | Completed | - | Completed | - | Completed | - | Completed | 2026-03-12 | Completed | 2026-05-18 | Completed | 2026-05-18 | Completed | 2026-07-29
18 | Sub Supplier PPAP Approvals | Completed | 2025-12-02 | Completed | - | Completed | - | Completed | - | Completed | - | Completed | - | Completed | 2026-03-12 | Completed | 2026-05-18 | Completed | 2026-05-18 | Completed | 2026-07-29
19 | Dimensional Results | Completed | 2025-12-02 | Completed | - | Completed | - | Completed | - | Completed | - | Completed | - | Completed | 2026-03-12 | Completed | 2026-05-18 | Completed | 2026-05-18 | Pending | 2026-07-03
20 | Material Certifications | Completed | 2025-12-02 | Completed | - | Completed | - | Completed | - | Completed | - | Completed | - | Completed | 2026-03-12 | Completed | 2026-05-18 | Completed | 2026-05-18 | Pending | 2026-07-03
21 | Shipping / Packaging | Completed | 2025-12-02 | Completed | - | Completed | - | Completed | - | Completed | - | Completed | - | Completed | 2026-03-12 | Completed | 2026-05-18 | Completed | 2026-05-18 | Completed | 2026-07-29
22 | Capability Studies | Completed | 2025-12-02 | Completed | - | Completed | - | Completed | - | Completed | - | Completed | - | Completed | 2026-03-12 | Completed | 2026-05-18 | Completed | 2026-05-18 | Completed | 2026-07-29
23 | SP12 (Containment) | Completed | 2025-12-02 | Completed | - | Completed | - | Completed | - | Completed | - | Completed | - | Completed | 2026-03-12 | Completed | 2026-05-12 | Completed | 2026-05-06 | Pending | 2026-06-03
24 | DVP&R | Completed | 2025-12-02 | Completed | - | Completed | - | Completed | - | Completed | - | Completed | - | Completed | 2026-03-12 | NA | NA | NA | NA | NA | NA
25 | Run at Rate | Completed | 2025-12-02 | Completed | - | Completed | - | Completed | - | Completed | - | Completed | - | Completed | 2026-03-12 | Completed | 2026-05-12 | Completed | 2026-05-25 | Completed | 2026-06-03
26 | Launch Readiness Review | Completed | 2025-12-02 | Completed | - | Completed | - | Completed | - | Completed | - | Completed | - | Completed | 2026-03-12 | Completed | 2026-05-12 | Completed | 2026-05-25 | Completed | 2026-08-01
27 | Interim approval action register | Completed | 2025-12-02 | Completed | - | Completed | - | Completed | - | Completed | - | Completed | - | Completed | 2026-03-12 | Completed | 2026-05-12 | Completed | 2026-05-25 | Completed | 2026-08-01
28 | Interim Submit | Completed | 2025-12-02 | Completed | - | Completed | - | Completed | - | Completed | - | Completed | - | Completed | 2026-03-19 | Completed | 2026-05-07 | Completed | 2026-05-25 | Completed | 2026-08-01
29 | Interim approved | Completed | 2025-12-02 | Completed | - | Completed | - | Completed | - | Completed | - | Completed | - | Completed | 2026-03-19 | Completed | 2026-05-20 | Completed | 2026-05-19 | Pending
30 | Full Submit | Completed | 2025-12-02 | Completed | - | Completed | - | Completed | - | Completed | - | Completed | - | Completed | 2026-03-19 | Completed | 2026-05-20 | Completed | 2026-05-25 | Pending
31 | Approval | Completed | 2025-12-02 | Completed | - | Completed | - | Completed | - | Completed | - | Completed | - | Completed | 2026-03-19 | Pending | 2026-05-25 | Pending | 2026-05-25 | Pending
32 | IMDS | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed | 2026-05-26

## status
Part No. 6128 PPAP has been fully uploaded. Final submission is pending as the customer final submit option is not yet available. Once the option is enabled, I will complete the final submission. Customer due date is 15-Jul-2026.
Current Status: Waiting for customer to enable the Final Submit option.